## Sheet1
Sprint 1
Task	Category	Story Points	Developer
Set up server		1	Ian
Write puppet module to install go with appropriate modules	Landing Zone	2	Raymond
Write queries for inserting data to the DB		3	Ian
Decode packets with proper error handling		3	Raymond
Accept and handle socket connections	API	1	Raymond
Code URL parsing for RESTful API		2	Raymond
Accept and handle HTTP connections		2	Ian
Build query, execute and return JSON results	Database	3	Ian
Write puppet module for postgres		2	Raymond
Migrate schema from MySQL to Postgres		3	Ian
Sprint 1 Completed		2
Sprint 1 Total		22

## Sheet2
Date	Points Completed	Total Points
10/03/14	0	0
10/21/14	2	21
10/28/14	8	22
Burnup Chart
Date
Story Points